## Timeline Comparison
The KSIMC of London — Election & AGM Timeline 2026
Two routes from 8 April 2026 — all dates are the LATEST permissible
# | Milestone | Route A ⚠️ AGM Sun 7 Jun (tight) | Route B ★ AGM Sun 14 Jun (recommended)
1 | EGM notice sent by email | Wed 8 Apr ⏰ | Sat 10 Apr ⏰
2 | EGM held — Commissioners elected | Fri 1 May (or Sun 3 May) | Sun 3 May
3 | Constitutional amendments deadline (members submit to Hon Sec) | Sun 26 Apr | Sun 3 May ⚠️ Same day as EGM
4 | Nominations open (set by Electoral Commission) | ~Mon 5 May | Mon 4 May
5 | Member register snapshot | ~Mon 4 May | Sun 10 May
6 | Register provided to Commission | ~Thu 8 May | Thu 14 May
7 | Nominations close (latest) | Fri 9 May ⏰ | Fri 16 May ⏰
8 | AGM notice + audited accounts sent | Fri 15 May ⏰ | Fri 22 May ⏰
9 | Candidate details circulated | Fri 15 May | Fri 22 May
10 | Motions deadline (members) | Fri 22 May ⏰ | Fri 29 May ⏰
11 | Hustings (if President contested) | Sat 23 May | Sat 30 May
12 | 🗳 ELECTION DAY (Sunday) | Sun 24 May | Sun 31 May
13 | Motions circulated to members | Tue 26 May | Tue 2 Jun
14 | 📋 AGM — New EC takes office | Sun 7 Jun | Sun 14 Jun
⏰ = Hard deadline (constitutional). Miss this date and the route is no longer viable.
⚠️ Route A is high-risk: Electoral Commission has only 3–6 days after EGM to organise before deadlines hit.
★ Route B is recommended: comfortable slack throughout. Commission has ~2 weeks to prepare.
All notices sent by email are deemed received 24 hours after sending (Cl. 17.3.1). "Clear days" exclude both the day of receipt and the day of the event (Cl. 20.1).
Based on the Constitution of The KSIMC of London & Election Rules · Updated 9 April 2026

## Route B — Recommended
Route B ★ — EGM → AGM Sun 14 Jun 2026 (Recommended)
Date | Event | Notes
Sat 10 Apr ⏰ | EGM notice sent | 21 clear days required. Last possible send date for EGM on Sun 3 May.
Sun 3 May | EGM — Commissioners elected | 5 commissioners elected by secret ballot. Commission elects its own Chairperson.
Sun 3 May | Amendments deadline | ⚠️ Same day as EGM. Members submit to Hon Secretary (Cl. 18.1).
Mon 4 May | Nominations open | Electoral Commission makes nomination papers available.
Sun 10 May | Member register snapshot | Register correct as at 20 clear days before Election.
Thu 14 May | Register to Commission | Hon Sec provides register 15 clear days before Election.
Fri 16 May ⏰ | Nominations close | Latest date: 14 clear days before Election Sun 31 May.
Fri 22 May ⏰ | AGM notice + accounts sent | 21 clear days before AGM. Include audited accounts (Cl. 12.9).
Fri 22 May | Amendments circulated | 21 clear days' notice to members (Cl. 18.3).
Fri 22 May | Candidate details circulated | Names, CVs, manifestos — 7 clear days before Election.
Fri 29 May ⏰ | Motions deadline | Members must submit 14 clear days before AGM.
Sat 30 May | Hustings | Mandatory if President contested. At least 1 day before Election.
Sun 31 May | 🗳 ELECTION DAY | Polling 10:30–19:30 at Imambara Building. All commissioners present.
Tue 2 Jun | Motions circulated | 10 clear days before AGM (Cl. 7.3).
Sun 14 Jun | 📋 AGM | New EC takes office at conclusion of AGM.